## Sheet1
Name | Todo | Importance | Difficulty | Priority
Document tracability? | 1 | 5 | 1 | 5
Investigate graph issue: redundant append | 1 | 3 | 1 | 3
Instument files refer to external cal source | 1 | 5 | 3 | 1.6667
Freeze if point moves during scroll | 1 | 5 | 3 | 1.6667
README.md | 1 | 1 | 1 | 1
Miscellanious Todos | 1 | 1 | 1 | 1
mK and uK self-heating checks | 1 | 2 | 2 | 1
Validate software? | 1 | 3 | 3 | 1
MBW DP30 | 1 | 2 | 3 | 0.66667
F17 Bridge | 1 | 2 | 3 | 0.66667
Setup.py? | 1 | 2 | 3 | 0.66667
Fix autosize columns? | 1 | 1 | 5 | 0.2
Change autoprofile table size | 1 | 1 | 5 | 0.2
"New Set" cancel | 0 | 5 | 1 | 0
Move to point N | 0 | 5 | 1 | 0
Graph transforms | 0 | 5 | 1 | 0
Report #s and dates | 0 | 5 | 1 | 0
Cancel load profile | 0 | 5 | 1 | 0
Change file saving to fixed address | 0 | 4 | 1 | 0
"Writing" on screen | 0 | 4 | 1 | 0
Details draw from job | 0 | 4 | 1 | 0
Mean/Stdev not tied to N | 0 | 4 | 1 | 0
Autoprofile first cell filename | 0 | 4 | 1 | 0
3900 Humidity Generator | 0 | 4 | 1 | 0
Update graphs more often | 0 | 3 | 1 | 0
Reset autoprofile | 0 | 3 | 1 | 0
Restart point | 0 | 3 | 1 | 0
Autoprofile starting at second point | 0 | 3 | 1 | 0
No resume until waiting | 0 | 3 | 1 | 0
Put the code on Github | 0 | 5 | 2 | 0
Autoprofile not writing | 0 | 5 | 2 | 0
Time in minutes | 0 | 5 | 2 | 0
Version number | 0 | 2 | 1 | 0
Change explicit list access to using .get() | 0 | 4 | 2 | 0
Generate graphs automatically | 0 | 4 | 2 | 0
Remind if instrument calibration due | 0 | 4 | 2 | 0
F250 Bridge | 0 | 4 | 2 | 0
Time/Assured on screen | 0 | 4 | 2 | 0
Check setpoints are set | 0 | 4 | 2 | 0
Open files from specific folders | 0 | 5 | 3 | 0
Mensor measurement E issue | 0 | 5 | 3 | 0
Save points | 0 | 3 | 2 | 0
Job names | 0 | 3 | 2 | 0
Print current point on screen | 0 | 3 | 2 | 0
Produce sensor file | 0 | 3 | 2 | 0
Autoprofile set on load | 0 | 3 | 2 | 0
Julabo FP79 | 0 | 4 | 3 | 0
Mensor CPT9000 | 0 | 4 | 3 | 0
SH2 Chilled Mirror | 0 | 4 | 3 | 0
SHX Chilled Mirror | 0 | 4 | 3 | 0
S8000 Chilled Mirror | 0 | 4 | 3 | 0
HP Mux | 0 | 4 | 3 | 0
Nanovoltmeter | 0 | 4 | 3 | 0
Record "name" rather than "id" | 0 | 4 | 3 | 0
Transform data | 0 | 4 | 3 | 0
Points files | 0 | 4 | 3 | 0
Graph names | 0 | 4 | 3 | 0
Detract graphs | 0 | 4 | 3 | 0
μK | 0 | 4 | 3 | 0
Put transform on display | 0 | 5 | 4 | 0
Autoprofile crash | 0 | 5 | 4 | 0
Streamline file saving | 0 | 2 | 2 | 0
Graph legend should display names, not inst/op | 0 | 3 | 3 | 0
Autoprofile controls | 0 | 3 | 3 | 0
Save locally & to I Drive | 0 | 3 | 3 | 0
- means "don't write" | 0 | 3 | 3 | 0
mK | 0 | 4 | 4 | 0
Source file (last N points) | 0 | 4 | 4 | 0
Graph multiple ys | 0 | 5 | 5 | 0
Kill graphs | 0 | 4 | 5 | 0
Move autoprofile checks to insturment files | 0 | 3 | 4 | 0
Scroll bar issues | 0 | 3 | 4 | 0
Add references | 0 | 3 | 4 | 0
Comment points files | 0 | 3 | 4 | 0
Autoprofile actions/actionwrite lists | 0 | 3 | 4 | 0
Clear comment box after points are recorded | 0 | 2 | 3 | 0
Fix datafile filenames | 0 | 2 | 3 | 0
Autoprofile control loops | 0 | 2 | 4 | 0
Rotation and translation stages | 0 | 2 | 4 | 0
2900 fan speed? | 0 | 1 | 3 | 0