## Sheet1
Name | Todo | Importance | Difficulty | Priority
Floating graphs/kill graphs | 1 | 4 | 2 | 2
Time in minutes | 1 | 2 | 1 | 2
Graph multiple ys | 1 | 5 | 3 | 1.6667
Autoprofile set on load | 1 | 3 | 2 | 1.5
Job names etc. | 1 | 3 | 2 | 1.5
Last/next N button | 1 | 3 | 2 | 1.5
Mensor CPT9000 | 1 | 4 | 3 | 1.3333
μK | 1 | 4 | 3 | 1.3333
Print current point on screen | 1 | 3 | 3 | 1
Save locally & to I Drive | 1 | 3 | 3 | 1
3900 Humidity Generator | 1 | 2 | 2 | 1
Add references | 1 | 3 | 4 | 0.75
MBW DP30 | 1 | 2 | 3 | 0.66667
Fix datafile filenames? | 1 | 2 | 3 | 0.66667
F17 Bridge | 1 | 2 | 3 | 0.66667
Setup.py | 1 | 2 | 3 | 0.66667
Load a sensor file? | 1 | 2 | 4 | 0.5
Miscellanious Todos | 1 | 1 | 3 | 0.33333
Graph transforms | 0 | 5 | 1 | 0
Report #s and dates | 0 | 5 | 1 | 0
Details draw from job | 0 | 4 | 1 | 0
Mean/Stdev not tied to N | 0 | 4 | 1 | 0
Autoprofile starting at second point | 0 | 3 | 1 | 0
Put the code on Github | 0 | 5 | 2 | 0
Autoprofile not writing | 0 | 5 | 2 | 0
F250 Bridge | 0 | 4 | 2 | 0
Produce sensor file | 0 | 3 | 2 | 0
SH2 Chilled Mirror | 0 | 4 | 3 | 0
SHX Chilled Mirror | 0 | 4 | 3 | 0
S8000 Chilled Mirror | 0 | 4 | 3 | 0
HP Mux | 0 | 4 | 3 | 0
Nanovoltmeter | 0 | 4 | 3 | 0
Record "name" rather than "id" | 0 | 4 | 3 | 0
Transform data | 0 | 4 | 3 | 0
Points files | 0 | 4 | 3 | 0
Put transform on display | 0 | 5 | 4 | 0
Autoprofile crash | 0 | 5 | 4 | 0
mK | 0 | 4 | 4 | 0
Source file (last N points) | 0 | 4 | 4 | 0
Comment points files | 0 | 3 | 4 | 0